## Sheet1
User Story | Tasks | 2018-02-15 | 2018-02-16 | 2018-02-17 | 2018-02-18
As a user, I can create an account where I must enter my name, major and all classes in my major. | Code the methods | 10 | 5 | 0 | 0
| Design the ui | 3 | 0 | 0 | 0
| Automate tests | 4 | 4 | 4 | 0
As a user, I will have the option to view my current major. | Code the methods | 4 | 0 | 0 | 0
| design the ui | 2 | 0 | 0 | 0
As a user, I can select to change my major where I must enter a new major and classes. | Code the methods | 8 | 5 | 0 | 0
| design the ui | 3 | 2 | 0 | 0
As a user, I can check my progress by viewing the classes I have finished and not finished. | Code the methods | 4 | 0 | 0 | 0
| design the ui | 2 | 0 | 0 | 0
As a user, I can delete the current user and start over from scratch. | Code the methods | 3 | 3 | 2 | 0
User Story | Tasks | 2018-02-23 | 2018-02-26 | 2018-03-01 | 2018-03-08 | 2018-03-18
As a student, I will be able to add a semester to my course history | Code the methods | 12 | 11 | 10 | 2 | 0
| Design the ui | 4 | 3 | 3 | 1 | 0
As a user, I will be able to add classes to each semester | Code the methods | 15 | 15 | 15 | 15 | 3
| Design the ui | 5 | 5 | 5 | 5 | 1
As a user, I will be able to add all necessary course information and final grades to calculate overall GPA | Code the methods | 15 | 15 | 15 | 15 | 13
| Design the ui | 5 | 5 | 5 | 5 | 5
As a user, I will have the ability to add grades for each class and specify the weight | Code the methods | 15 | 15 | 15 | 15 | 10
| Design the ui | 5 | 5 | 5 | 5 | 5
As a student, I will be able to predict my final grade based on potential grades I input and change based on different outcomes. | Code the methods | 15 | 15 | 15 | 15 | 15
| Design the ui | 5 | 5 | 5 | 5 | 5